## Slide 1: Agile plan for three months APS
Authors:
Marina Nikolic and Miroslav Misljenovic

## Slide 2: Collaboration teams and their leaders
MATF | Miroslav Misljenovic
RT-RK | Marina Nikolic
EED | Milos Stojanovic
OBLO | Djordje Pesic
TTTECH | Jovan Petrovic

## Slide 3: Sprint
Generate reports on road conditions in Serbia
Finish algorithm design, analysis and documentation for three systems
Implement first version of each system (unoptimized, untested)
Test first version of one sensor per system
Handle deadline braking issues
Publish two papers, as part of dissemination

## Slide 4: 12th month: December, 2018. cross-section of the situation on day: 12.12.2018.
WP number | WP name | Task number | Task Description | Team | Team lead | Status on date of cross-section | Start date | Due date
4 | Detailed study on road conditions in Serbia | T1 | Generate statistical and detailed reports on damages of roads in Serbia | RT-RK | Marina Nikolic | WIP | 1.12 | 20.12
 |  | T2 | Generate statistical and detailed reports on quality on line markings of roads in Serbia |  |  | WIP | 1.12 | 15.12
 |  | T3 | Generate report on sections of roads in Serbia with inadequate lighting |  |  | Done | 1.12 | 10.12

## Slide 5: 12th month: December, 2018. cross-section of the situation on day: 12.12.2018.
WP number | WP name | Task number | Task description | Team | Team lead | Status on date of cross-section | Start date | Due date
5 | Software implementation | T4 | Finish algorithm for damage recognition system | MATF | Miroslav Misljenovic | Done | 1.12 | 7.12
 |  | T5 | Finish algorithm for side-line following system |  |  | Done | 1.12 | 7.12
 |  | T6 | Finish algorithm for car distance and speed system |  |  | Done | 1.12 | 7.12
 |  | T7 | Analysis of algorithms for damage recognition system |  |  | WIP | 8.12 | 15.12
 |  | T8 | Analysis of algorithms for side-line following system |  |  | WIP | 8.12 | 15.12
 |  | T9 | Analysis of algorithms for car distance and speed system |  |  | WIP | 8.12 | 15.12
 |  | T10 | Generate documentation on algorithms for damage recognition system |  |  | To do | 16.12 | 19.12
 |  | T11 | Generate documentation on for side-line following system |  |  | To do | 16.12 | 19.12
 |  | T12 | Generate documentation on for car distance and speed system |  |  | To do | 16.12 | 19.12
 |  | T13 | Implementation of improvement for visibility sensor | EED | Milos Stojanovic | To do | 20.12 | 30.12
 |  | T14 | Implementation of improvement for line visibility sensor |  |  | To do | 20.12 | 30.12
 |  | T15 | Implementation of improvement for recognition of cars shapes in Serbia and distance between them |  |  | To do | 20.12 | 30.12

## Slide 6: 13th month: January, 2019. cross-section of the situation on day: 18.1.2019.
WP number | WP name | Task number | Task Description | Team | Team lead | Status on date of cross-section | Start date | Due date
0 | Project Management | T1 | Coordinate dependency between tasks and mitigate consequences of block in case of problems | TTTech | Jovan Petrovic | WIP | 1.1 | 31.1
5 | Software implementation | T2 | Implementation of improvement for recognition of road damages shape and size | EED | Milos Stojanovic | Blocked Until done: T1, December | 1.1 | 15.1
 |  | T3 | Implementation of improvement for calculating distance between side-lines |  |  | WIP | 5.1 | 20.1
 |  | T4 | Implementation of improvement for calculating optimal distance from cars in front and behind |  |  | WIP | 10.1 | 25.1
6 | Testing | T5 | Test improvement for visibility sensor | OBLO | Djordje Pesic | WIP | 15.1 | 20.1
 |  | T6 | Test improvement for line visibility sensor |  |  | Blocked Until done: T13, December | 15.1 | 20.1
 |  | T7 | Test improvement for recognition of cars shapes in Serbia and distance between them |  |  | To do | 20.1 | 28.1
7 | Dissemination | T8 | Publish one paper in Top Gear | RT-RK | Marina Nikolic | Done | 5.1 | 10.1

## Slide 7: 14th month: February, 2019. cross-section of the situation on day: 11.2.2019.
WP Number | WP name | Task number | Task description | Team | Team lead | Status on date of cross-section | Start date | Due date
0 | Project Management | T1 | Coordinate dependency between tasks and mitigate consequences of block in case of problems | TTTech | Jovan Petrovic | WIP | 1.2 | 28.2
5 | Software implementation | T2 | Implementation of improvement for road damages avoiding system | EED | Milos Stojanovic | Done | 1.2 | 12.2
 |  | T3 | Implementation of improvement for calculating optimal distance from side-lines |  |  | WIP | 8.2 | 20.2
 |  | T4 | Implementation of improvement for speed system for maintaining distance |  |  | To do | 13.2 | 25.2
7 | Dissemination | T5 | Publish one paper in Road & Track | RT-RK | Marina Nikolic | Done | 5.2. | 10.2

## Slide 8: It’s not the will to win that matters, everyone has that. It’s the will to prepare to win that matters. Paul Bryant