## Slide 1: H2020 : APS Autopilot cars for roads in Serbia
Type of funding scheme: STREP
Work programme topics addressed:
Internet of Things - ICT-27-2018-2020
Name of the coordinating person:
Miroslav Misljenovic, Marina Nikolic
E-mail:
mr12260@alas.matf.bg.ac.rs
mr12095@alas.matf.bg.ac.rs

## Slide 2: Participants:
Miroslav Misljenovic | MATF | Serbia
Marina Nikolic | RT-RK | Germany
Milos Stojanovic | EED | Netherlands
Djordje Pesic | OBLO | Serbia
Jovan Petrovic | TTTECH | Austria

## Slide 3: About project… WHY?
Serbia…
So hard to drive…
  Holes on the roads
  Inadequate marking
  Poor lighting of individual sections
How to automatize something that unpredictable?
Current technologies
  Recognize only quality and unimpaired signalling
  Impossible to apply in Serbia

## Slide 4: About project… HOW?
An idea struck in our minds…
Adapt autopilot software for roads in Serbia
and implement it on vehicles imported from Korea
We want to be better…
  Improving the system for identifying and avoiding holes and other road damages
  Improving the system for side-line following, in straight driving, curves and turning
  Improving the system for distance measuring and speed optimisation

## Slide 5: About project… FOR WHO?
We want
More people driving autopilot cars!
More importantly we want…
More people driving!!!
Give chance to…
  Blind and visually impaired people
  People with disabilities
Safety first:
  One test saves on life!
  Testing… and more testing…

## Slide 6: Progress beyond the state-of-the-art
Many researches have been conducted…
Not one applicable on roads like the ones in Serbia…
Here we go beyond state of the art!
TESLA:
    Most advanced technologies
    In top 5 selling autopilot cars
    Remarkable properties of cars with autopilot
    But…
    Unreliable and dangerous even on more quality roads then the ones in Serbia.
Keep good properties, but correct the flaws.

## Slide 7: Work packages - table
Work package No | Work package title | Type of activity | Lead partic no. | Lead partic. short name | Person-months | Start month | End month
WP0 | Project management | MGT | 2 | RT-RK | 48 | M1 | M21
WP1 | Generating use cases | RTD | 1 | MATF | 8 | M2 | M3
WP2 | Import vehicles from South Korea | RTD | 5 | TTTECH | 4 | M4 | M5
WP3 | Obtain software from Tesla | RTD | 3 | EED | 8 | M4 | M5
WP4 | Detailed study on road conditions in Serbia | RTD | 5 | TTTECH | 70 | M6 | M12
WP5 | Software implementation | RTD | 1 | MATF | 160 | M10 | M18
WP6 | Testing | RTD | 4 | OBLO | 50 | M13 | M19
WP7 | Dissemination | DEM | 2 | RT-RK | 24 | M13 | M24
 | TOTAL |  |  |  | 372 |  | 

## Slide 8: Work packages - Gantt chart
 | Months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
WP0 Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP1 Generating use cases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP2 Import vehicles from South Korea |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP3 Obtain software from Tesla |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP4 Detailed study on road conditions in Serbia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP5 Software implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP6 Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP7 Dissemination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 9: Work packages – Pert chart

## Slide 10: Deliverables
Del. no. | Deliverable name | WP no. | Nature | Dissemi-nation level | Delivery date (proj. month)
D0.1 | Progress report for the three months of work | 0 | R | PU | M3
D0.2 | Progress report for the nine months of work | 0 | R | PU | M9
D0.3 | Progress report for the fifteen months of work | 0 | R | PU | M15
D0.4 | Progress report of whole project | 0 | R | PU | M24
D1 | Documentation of use cases | 1 | R | CO | M4
D2 | Confirmation on import success | 2 | R | PP | M6
D3 | Confirmation on Tesla’s software receiving success | 3 | R | PP | M6

## Slide 11: Deliverables
Del. no. | Deliverable name | WP no. | Nature | Dissemi-nation level | Delivery date (proj. month)
D4 | Report on detailed study on Serbian roads | 4 | R | CO | M13
D5.1 | Documented code | 5 | R | CO | M14
D5.2 | Final version of software implementation | 5 | P | CO | M18
D6.1 | Documented testing procedures | 6 | R | CO | M14
D6.2 | Report on testing results | 6 | R | PU | M20
D7.1 | Number of participants at automotive seminars and sessions | 7 | D | PU | M24
D7.2 | Number of car shows organized | 7 | D | PU | M24
D7.3 | Number of arcticles in international car magazines | 7 | D | PU | M24

## Slide 12: Milestones
Milestone number | Milestone name | Work package(s) involved | Expected date | Means of verification
M0.1 | Checking on optimization of the reporting processes involved in the project (deadlines) | WP0 | M6 | 
M0.2 | Checking on optimization of the control processes involved in the project | WP0 | M12 | 
M0.3 | Checking on optimizing finances of the project | WP0 | M12 | 
M1.1 | Checking on opinion of beneficiaries on the need for the generated applications | WP1 | M3 | 
M1.2 | Checking on opinion of beneficiaries about the functionalities provided | WP1 | M4 | 
M2.1 | Checking if imports are done in arranged deadlines | WP2 | M5 | 
M2.2 | Checking if needed licences are obtained | WP2 | M5 | 
M3.1 | Checking if needed licences are obtained | WP3 | M5 | 
M4.1 | Checking if list of all possible problems on Serbian roads is made properly | WP4 | M13 | 

## Slide 13: Milestones
Milestone number | Milestone name | Work package(s) involved | Expected date | Means of verification
M5.1 | Checking on system for damage recognition | WP5 | M18 | System can detect and avoid road damages off any size and types.
M5.2 | Checking on system for side-line following | WP5 | M18 | System can maintain required distance from each side-line in straight driving and in both left and right curves and turning.
M5.3 | Checking on system for car distance | WP5 | M18 | System can measure distance from both cars in front and behind and optimize speed to keep it constant.
M5.4 | Checking if software covers statistically significant number of different road issues | WP5 | M18 | 
M6.1 | Checking if test cases are developed according to the needs of the beneficiary industry | WP6 | M13 | 
M6.2 | Checking if all 12 test combinations passed successfully. | WP6 | M20 | 
M7.1 | Checking on number of papers presented at most famous international car magazines | WP7 | M24 | Number must match plan: one per each month dissemination is done, 8 in total
M7.2 | Checking on number of participants at automotive seminars and sessions | WP7 | M24 | Number must match plan: one of each kind, in each dissemination section, 4 participations in total

## Slide 14: Management structure

## Slide 15: Resources
Some expenses:
  Import expenses estimated on E260K
  Licence obtaining resources estimated on E100K
  Software implementation resources estimated on E200K
  Testing equipment resources estimated on E350K
Overall: 4.000.000,00 euro

## Slide 16: Impact and dissemination
Positive impact on the economy of all car producers
Strong impact on each partner
People with disabilities will drive
Commercial and scientific impact
Posting an example to other countries, Europe-wide
Dissemination is planed through
  Sessions and seminars
  Car shows
  Media: local TV and radio stations, international car magazines, ...

## Slide 17: Ethical issues
No direct ethical, legal, social and safety issues
Just in case, we will form:
Ethical committee
Because:
  There is no right way to do a wrong thing…
  Harold S. Kushner

## Slide 18: Thank You For Your Attention !!!